## Milestone_1
Project: |  | Barb's Dungeon
Date | Reference # | Milestone | Milestone Goal | Task | Task # | Responsible Team Member | Dependencies | % Completed | Comments
2024-02-17 | D1 | Getting Started | Begin implementing terrain | Begin PGE Dungeon | 7a | Geoffrey | None | 100 | Research algorithms for generating random floors + start implementation
|  |  | generation, simple character | Basic Character Movement | 1a | Emi | None | 100 | Tempoary assets for testing
|  |  | movement, stats (HP, Mana), | Basic Character Combat | 1a | Emi | None | 100 | Tempoary assets for testing
|  |  | look into character designs, | Audio Research | 9a | Danny | None | 100 | Look at Darren Korb
|  |  | and audio inspirations | Character Model/Select | A1 | Heather | None | 100
|  |  |  | Start Room Type Design | 7a | ALL | None | 100
|  |  |  | Create Stats | 1d,1f | Zach | None | 100
|  |  |  | Style of UI Elements | E8 | Eli | None | 100
2024-02-24 | D2 | Finalize Basic Design of Game | Finalize Room Types for PGE, | Start Character Animations | B1-B4 | Heather | None | 100
|  |  | design for UI Elements, begin | Finalize Room Designs | 7a | ALL | None | 50
|  |  | adding variability to movement/ | PGE Dungeon | 7a | Geoffrey | None | 100 | Generate random floors
|  |  | combat based on class, first | Variation to Movement | 1a | Emi | None | 90 | Think about rolling
|  |  | samples of music, sprite sheet | 4 Core Combat Strikes | 1a | Emi | None | 100
|  |  | and begin animations | Music/Audio Samples | 9a | Danny | None | 100 | Think about finding or making our samples
|  |  |  | Finalize UI Elements | E8 | Zach | None | 60
2024-03-02 | F001 | Playable First Floor | Room types incorperated into | PGE Dungeon + Rooms | 7a | Geoffrey | None | 50 | Generate random floors using finalized rooms
|  |  | PGE Dungeon, Character | Finish A Character Animations | B1-B4 | Heather | None | 100
|  |  | Selections, Some variablility | First Floor Music | 9a | Danny | None | 100
|  |  | based on character, basic enemy, | UI For Character Select | E8 | Eli | None | 100
|  |  | first floor music | Finalize Core Combat | 1a | Emi | None | 100
|  |  |  | Stats linked to Combat | 1a | Zach | E8 | 25 | Link combat strike to cooldown of mana
|  |  |  | Basic Enemy | 2a | Emi | None | 20 | Interact with HP stats when hit
Plan for next week
vision system
inventory UI
item drop system
rolling animation

## Milestone_2
Project: |  | Barb's Dungeon
Date | Reference # | Milestone | Milestone Goal | Task | Task # | Responsible Team Member | Dependencies | % Completed | Comments
2024-03-16 | D1 | Finish up demo features | Finalize and start on system | Start Stamina | 1d | Emi | None | 100 | should only take 20 minutes or less to add this
|  |  | that are needed for the verticle | Basic enemies | 2b, 2a | Emi | None | 100
|  |  | slice demo. The goal of this week | Start Vision System | 2b | Emi | None | 100
|  |  | is to have all the major systems | Start Audio System | 2b | Emi | None | 100
|  |  | at least present in the game. This | Implementation Level 1 Rooms | 7a | Geoffrey | None
|  |  | will set us up to test these systems | Second Floor Music Production | 9a | Danny | None | 20
|  |  | before further development. | Start Skill Tree system | 5b | Geoffrey | None
|  |  |  | Rogue Art Sprite Sheet | 10a | Heather | None
|  |  |  | Test and iterate on values | 5c | Zach | None | 100 | Add in default stats and upgraded stats per level up for each class
|  |  |  | Look over and fix all discovery feedback from first checkpoint | n/a | Zach | None | 100 | Updated the Narrative, Game Loops, Feature List, Technical Design Doc, and Asset List
|  |  |  | Start ability for some characters (knight) | 7a | Geoffrey | None
|  |  |  | Designing Level 1 Rooms | 7a | Eli | None
2024-03-23 | D2 | Finalize Basic Design of Game | The goal is to finalize now the | Finalize In Game UI Elements | 11a | Zach | None | 100
|  |  | systems and polish what worked | Start on UI elements for menus | 11a | Zach | None | 100
|  |  | well. Changes need to be made | Complete Second Floor Music | 9a | Danny | None
|  |  | to systems that feel off and the | Start on sound effects | 9a | Danny | None
|  |  | game should be ready for the | Finalize character skill tree | 5b | Geoffrey | None
|  |  | vertical | Polish knight abilities | 5b | Geoffrey | None
|  |  |  | Implement basic items | 3a | Emi | None | 50
|  |  |  | Finalize Vision System | 2b | Emi | None | 100
|  |  |  | Finalize Basic enemies | 2b,2a | Emi | None | 100
|  |  |  | Finalize Stamina System | 2b | Emi | None | 50
|  |  |  | Finalize Audio System | 2b | Emi | None | 100
|  |  |  | Start and finish NPC system | 7c | Geoffrey | None
|  |  |  | Wizard art sprite sheet | 10a | Heather | None
|  |  |  | Design item placements | 7c | Eli | None
|  |  |  | Design interactable placements | 7c | Eli | None
|  |  |  | Start mage abilties | 5b | Geoffrey | None
2024-03-30 | F001 | Playable First Floor | Complete the playable build of the | Add more details to skills, focusing on time active and damage dealt | 5b | Zach | None | 100
|  |  | first floor of the game with stats, | Stats linked to combat | 1a, 1b, 1c | Zach | None | 100 | Make crits do 2x normal damage.
|  |  | skills, music, and combat. | Start Boss 1 Music | 9a | Danny | None
|  |  | Make further advancements on | Continue on sound effects | 9a | Danny | None
|  |  | finding/creating art, including | Start Boss 1 Developement | 2a, 2b, 2c | Geoffrey | None
|  |  | animations and enemy | Finalize Mage abilities | 5b | Geoffrey | E8
|  |  | models. | Start and finish haste system | 2c | Emi | None | 0
|  |  |  | Start and finish inventory system | 3a | Emi | None | 50
|  |  |  | Start and finish rest system | 7d | Emi | None | 0
|  |  |  | Start dialogue system | 7c | Emi | None | 10
|  |  |  | Design enemy spawn rate | 7c | Eli | None
|  |  |  | Design enemy placement | 7c | Eli | None
|  |  |  | Continue implementions of sprites | 10a | Emi | None | 100
|  |  |  | Implement basic interactable | 3a | Emi | None | 0
|  |  |  | Ranger art sprite sheet | 10a | Heather | None
|  |  |  | Finalize room generation for level 1 | 7a | Geoffrey | None
https://barbsdungeon.atlassian.net/jira/software/projects/TP/boards/2