## Sheet1
Risk Registry
|  | Area of Risk |  |  | Status | Probability | Impact | Priority | Mitigation | Recovery
ID # | Name | (Discipline or Feature) | Quick Description | Owner | (Open/Closed) | (1-5) | (1-5) | (Prob. * Impact) | (How to reduce/remove the risk) | (How to fix the problem if it occurs)
1 | Group member medical procedure | Programming | Emi is going in for a medical procedure on April 16th and is not sure what to expect. If recovery is worse then expected, it can effect timeline of the base game features. | Emi B. | Open | 2 | 3 | 6 | Emi will try to work ahead / plan for a lighter workload that week. | Geoffrey and Emi will work together to split any remaining work
2 | Dungeon Generation Integration | Level Generation | The current dungeon generation system is a seperate system from the base game that is being developed. The current system also has not been tested with designed rooms and mandated rooms. There is some risk in merging to master and ensuring the dungeons generation is fun/playable. | Geoffrey D. | Open | 2 | 5 | 10 | Merge in to master ASAP, and test with the movements of the base game. Also work on adding in the start/end rooms and some other example designed rooms and test the slice of the game. | Try redesigning the templated rooms and see if it fixes the playability. If needed, alter the algorithm of the dungeon generation (Less hallways perhaps). Or, remove all generated rooms and use only templated rooms instead.
3 | Group member going abroad | Music | One of the staff members in charge of writing and composing the music is going abroad. While abroad, there could be issues in finishing the music or working with team, largely due to time zone issues. | Danny | Open | 2 | 2 | 4 | Danny will work all the time when abroad, and has set out time slots to work on music when rest of team is awake. Danny has worked during spring break and finished ahead of schedule to help mediate issues that might come up that he needs to address while abroad. | Music will be backloaded as enough of the level samples have already been created for the demos. If worst comes to worst, Danny will work extra when he comes back to help catch up on schedule with music.